## Risk List
# | Date Identified | Description | Type | Impact | Probability | Magnitude
1 | Current | Limited scalability with MySQL. | Direct, Technical | 3 | 60 | 1.8
2 | Current | High costs and vendor lock-in with Amazon RDS. | Direct, Financial | 4 | 50 | 2
3 | Current | Less data consistency with MongoDB. | Direct, Technical | 3 | 70 | 2.1
4 | Current | Difficulty ensuring consistent design across devices with responsive design. | Indirect, Technical | 2 | 50 | 1
5 | Current | Challenges adapting complex features for desktop with mobile-first design. | Indirect, Technical | 3 | 60 | 1.8
6 | Current | Learning curve with MVC using Laravel. | Indirect, Technical | 3 | 50 | 1.5
7 | Current | Less community support for Python with MySQLdb. | Indirect, Technical | 2 | 60 | 1.2
8 | Current | PDO being specific to PHP limits flexibility with other languages. | Direct, Technical | 2 | 50 | 1
9 | Current | High development and maintenance costs with native app development. | Direct, Financial | 4 | 70 | 2.8
10 | Current | Limited access to device features and less native feel with Progressive Web Apps. | Direct, Technical | 3 | 60 | 1.8

## Mitigation Strategy
# | Risk Addressed | Owner | Mitigation Strategy
1 | MySQL scalability | Development Team | Implement database clustering and plan for future scalability or migration.
2 | Amazon RDS costs | Development Team | Prepare for higher initial costs and analyze total cost of ownership with Amazon RDS.
3 | MongoDB consistency | Development Team | Use hybrid database models to ensure data consistency in MongoDB.
4 | Responsive design consistency | Development Team | Employ CSS frameworks like Bootstrap for consistent UI across platforms.
5 | Mobile-first design adaptation | Development Team | Design with mobile constraints in mind and then scale up for desktop features.
6 | MVC Laravel learning curve | Development Team | Offer training and use scaffolding tools to mitigate MVC Laravel learning curve.
7 | Python MySQLdb support | Development Team | Engage more with Python communities or consider more supported libraries.
8 | PDO PHP flexibility | Development Team | Use universal database connectivity libraries or middleware for flexibility.
9 | Native app costs | Development Team | Adopt cross-platform development frameworks to reduce costs and unify codebase.
10 | PWA device features | Development Team | Choose technologies like Flutter or React Native to enhance PWA capabilities.